## Product Backlog
Hotel Reservation Management System - Product Backlog
Scope baseline: one medium-sized hotel, approximately 80 rooms, employee-only web system.
Sprint 1 items are marked Ready for Review. Change them to Done only after supervisor acceptance. The backlog includes required UML/documentation artifacts for Sprints 2-6.
ID | Backlog Item | Priority | Planned Sprint | Story Points | Dependencies | Related User Stories | Definition of Done | Status | Notes
PBI-01 | Approve project scope, assumptions, and exclusions | Must | 1 | 3 | — | — | Scope accepted and consistent across SRS, use cases, and ERD. | Ready for Review | Change to Done after Sprint 1 is accepted by the supervisor.
PBI-02 | Complete comparative analysis of five existing PMS products | Must | 1 | 5 | PBI-01 | — | Five official-source comparisons and a project conclusion are documented. | Ready for Review | Change to Done after Sprint 1 is accepted by the supervisor.
PBI-03 | Baseline functional and non-functional requirements | Must | 1 | 8 | PBI-01 | US-01–US-24 | All mandatory requirements are uniquely identified and reviewable. | Ready for Review | Change to Done after Sprint 1 is accepted by the supervisor.
PBI-04 | Prepare user stories and initial product backlog | Must | 1 | 5 | PBI-03 | US-01–US-24 | Stories have roles, value, acceptance conditions, priority, and sprint. | Ready for Review | Change to Done after Sprint 1 is accepted by the supervisor.
PBI-05 | Create UML use case model | Must | 1 | 3 | PBI-03 | US-01–US-24 | Actors and use cases match the documented roles and functions. | Ready for Review | Change to Done after Sprint 1 is accepted by the supervisor.
PBI-06 | Create initial ERD | Must | 1 | 5 | PBI-03 | US-01–US-23 | Entities support reservations, rooms, payments, statuses, and audit history. | Ready for Review | Change to Done after Sprint 1 is accepted by the supervisor.
PBI-07 | Initialize Git repository and project folder structure | Must | 2 | 2 | Sprint 1 approval | — | Repository contains meaningful initial commits and required directories. | Not Started
PBI-08 | Initialize Java 21 Spring Boot Maven project | Must | 2 | 3 | PBI-07 | — | Project builds and starts without errors. | Not Started
PBI-09 | Configure PostgreSQL connection and Flyway migrations | Must | 2 | 5 | PBI-08 | — | Application connects and creates the approved initial schema. | Not Started
PBI-10 | Implement layered package structure and base entities | Must | 2 | 5 | PBI-09 | — | Presentation, service, domain, and repository responsibilities are separated. | Not Started
PBI-11 | Implement authentication and role model | Must | 3 | 8 | PBI-10 | US-01; US-02; US-23; US-24 | Active users can log in; permissions are server-side enforced. | Not Started
PBI-12 | Implement room type, room, and rate CRUD | Must | 3 | 8 | PBI-10 | US-03; US-04; US-18 | Master data validates uniqueness, capacity, status, and historical preservation. | Not Started
PBI-13 | Implement guest CRUD and search | Must | 3 | 5 | PBI-10 | US-06; US-07 | Guests can be created, found, updated, and duplicate warnings are shown. | Not Started
PBI-14 | Implement availability calculation service | Must | 3 | 8 | PBI-12 | US-05 | Date overlap, capacity, status, and maintenance rules are tested. | Not Started
PBI-15 | Implement reservation CRUD and booking reference generation | Must | 3 | 13 | PBI-13; PBI-14 | US-08; US-09; US-10 | Reservations and room lines persist transactionally with rate snapshots. | Not Started
PBI-16 | Add validation, exception handling, sample data, and unit tests | Must | 3 | 8 | PBI-11–15 | US-24 | Core rules have automated tests and understandable errors. | Not Started
PBI-17 | Develop employee web login and navigation | Must | 4 | 5 | PBI-11 | US-01; US-02; US-24 | Interface adapts to role permissions. | Not Started
PBI-18 | Develop room, rate, and guest management pages | Must | 4 | 8 | PBI-12; PBI-13 | US-03; US-04; US-06; US-07 | Authorized users can complete master-data workflows through the UI. | Not Started
PBI-19 | Develop availability and reservation pages | Must | 4 | 13 | PBI-14; PBI-15 | US-05; US-08; US-09; US-10 | Receptionist can search, create, modify, and cancel reservations. | Not Started
PBI-20 | Implement search, filtering, and pagination | Should | 4 | 5 | PBI-18; PBI-19 | US-05; US-07; US-20; US-22 | Lists remain usable with realistic historical data. | Not Started
PBI-21 | Implement physical room assignment | Must | 4 | 8 | PBI-14; PBI-15 | US-11 | Conflicting or incompatible assignments are prevented. | Not Started
PBI-22 | Implement check-in workflow | Must | 4 | 8 | PBI-21 | US-12 | All required rooms are assigned and ready; reservation status, actual time, and room occupancy statuses update transactionally. | Not Started
PBI-23 | Implement payment and balance tracking | Must | 5 | 8 | PBI-15 | US-13; US-14; US-22 | Deposits, payments, refunds, totals, and balances are correct and auditable. | Not Started
PBI-24 | Implement check-out workflow | Must | 5 | 8 | PBI-22; PBI-23 | US-15 | Final account is shown; reservation is checked out as one stay operation; assigned rooms become vacant and dirty. | Not Started
PBI-25 | Implement housekeeping work list and room-status history | Must | 5 | 8 | PBI-12; PBI-24 | US-16; US-17; US-18 | Housekeeping updates are visible to front desk and historically recorded. | Not Started
PBI-26 | Implement operational reports | Must | 5 | 8 | PBI-15; PBI-22; PBI-24 | US-19; US-20; US-21 | Occupancy, arrivals, departures, and in-house reports are available. | Not Started
PBI-27 | Implement financial reports | Must | 5 | 8 | PBI-23 | US-22 | Payments, refunds, revenue, and balances can be filtered and reconciled to reservation balances. | Not Started
PBI-28 | Implement audit log and review page | Must | 5 | 5 | PBI-11; core modules | US-23 | Significant actions are immutable and searchable by authorized roles. | Not Started
PBI-29 | Complete functional and integration tests | Must | 6 | 13 | PBI-17–28 | US-01–US-24 | Approved business scenarios execute successfully in automated or documented tests. | Not Started
PBI-30 | Optimize queries and correct defects | Must | 6 | 8 | PBI-29 | US-24 | Critical defects are resolved and target response times are measured. | Not Started
PBI-31 | Create Docker deployment and backup procedure | Must | 6 | 8 | PBI-29 | — | Application and database can be deployed in a clean environment. | Not Started
PBI-32 | Prepare user and administrator manuals | Must | 7 | 8 | Stable system | — | Manuals cover routine operation, roles, configuration, backup, and recovery. | Not Started
PBI-33 | Synchronize UML, database, and implementation documentation | Must | 7 | 5 | Stable system | US-01–US-24 | All diagrams and descriptions correspond to the actual application. | Not Started
PBI-34 | Prepare thesis draft and preliminary presentation | Must | 7 | 13 | PBI-32; PBI-33 | US-01–US-24 | Draft explains analysis, design, implementation, and testing. | Not Started
PBI-35 | Finalize application, thesis, presentation, and defense demo | Must | 8 | 13 | All previous items | US-01–US-24 | All artifacts are consistent and the system can be deployed and demonstrated from scratch. | Not Started
PBI-36 | Prepare initial software architecture diagram | Must | 1 | 2 | PBI-01 | — | Editable layered architecture diagram is consistent with the SRS and technology stack. | Ready for Review | Added during internal Sprint 1 review.
PBI-37 | Prepare UML Class Diagram | Must | 2 | 5 | PBI-10 | — | Class diagram represents main domain entities and relationships implemented in Sprint 2. | Not Started
PBI-38 | Prepare UML Package Diagram | Must | 2 | 3 | PBI-10 | — | Package diagram explains presentation, service, domain, and data-access responsibilities. | Not Started
PBI-39 | Prepare project installation and build guide | Must | 2 | 3 | PBI-08; PBI-09 | — | A clean environment can build, start, and connect the application to PostgreSQL. | Not Started
PBI-40 | Prepare UML Sequence Diagram | Must | 3 | 3 | Core business logic | — | Sequence diagram corresponds to one implemented key business interaction. | Not Started
PBI-41 | Prepare UML Activity Diagram | Must | 4 | 3 | Primary UI workflow | — | Activity diagram corresponds to an implemented primary user workflow. | Not Started
PBI-42 | Prepare UML Component Diagram | Must | 5 | 3 | Integrated modules | — | Component diagram represents implemented software components and dependencies. | Not Started
PBI-43 | Prepare UML Deployment Diagram | Must | 6 | 3 | PBI-31 | — | Deployment diagram represents the actual deployment environment. | Not Started
PBI-44 | Prepare deployment guide | Must | 6 | 3 | PBI-31 | — | Guide documents deployment, required versions, configuration, backup, and restore steps. | Not Started
PBI-45 | Add CSV export for selected reports | Should | 5 | 3 | PBI-26; PBI-27 | US-19; US-22 | Selected operational or financial reports can be exported to CSV. | Not Started

## Sprint Summary
Sprint Summary Dashboard
Sprint | Main Goal | Backlog Items | Total Points | Ready for Review | Done | Not Started | Progress
1 | Requirements Analysis and System Design | 7 | 31 | 7 | 0 | 0 | 50%
2 | Project Initialization and Software Architecture | 7 | 26 | 0 | 0 | 7 | 0%
3 | Core Business Logic Implementation | 7 | 53 | 0 | 0 | 7 | 0%
4 | Functional Expansion and User Interface | 7 | 50 | 0 | 0 | 7 | 0%
5 | Feature Completion and System Integration | 8 | 51 | 0 | 0 | 8 | 0%
6 | Quality Assurance and Deployment | 5 | 35 | 0 | 0 | 5 | 0%
7 | Documentation and Final Preparation | 3 | 26 | 0 | 0 | 3 | 0%
8 | Final Review and Pre-Defense | 1 | 13 | 0 | 0 | 1 | 0%

## Instructions
How to Use This Product Backlog
Step | What to Do | When | Important Rule
1 | Open the Product Backlog sheet. | At the start of every sprint. | Do not delete previous items.
2 | Filter Planned Sprint to the current sprint. | During sprint planning. | Use the filter arrow in the header row.
3 | Update Status using the drop-down list. | Whenever work state changes. | Use Ready for Review before supervisor approval; use Done only after acceptance.
4 | Update Dependencies if one item must wait for another. | When planning changes. | Reference the PBI identifier, for example PBI-14.
5 | Write short factual notes in the Notes column. | After feedback or scope changes. | Record what changed and why.
6 | Review the Sprint Summary sheet. | Before the Sprint Review. | The summary and chart update from backlog formulas in Excel.
7 | Save a new version before major changes. | After supervisor feedback. | Use versioned file names only for formal review copies; keep one current working file.